## PPA WKSHT
Potential Problem Analysis |  |  |  |  | Potential Problem Analysis
Identify Potential Problems |  |  | Identify Likely Causes | Take Preventive Action | Plan Contingent Action and Set Triggers
State the action |  |  | Consider causes for the potential problem | Take actions to address likely causes
List potential problems |  |  |  |  | Prepare actions to reduce likely effects | Set triggers for contingent actions
Potential Problems | Probability | Seriousness | Likely Causes | Preventive Actions | Contingent Actions | Triggers
What evidence do we have…?
What different deviations, decisions,
or plans are part of this concern?
What could cause the potential problem to occur?
What else could cause…?
When we do this, what could go wrong?
What problem could this action cause?
How likely is the problem?
What would be the impact?
What can we do to prevent this likely cause from happening?
What can we do to reduce the chances of this likely cause happening?
How can we keep this likely cause from creating the potential problem?
What is the end result to be achieved? Include an action word, a result, and a time frame.
Do we need further clarification?
Do we have a deviation? Is cause unknown?
Do we need to know the cause of a deviation?
Do we need to make a choice?
Do we have an action or plan to protect (enhance)?
What do we need to do about the concern?
What additional analysis is needed?
What needs to be done and when?
Who needs to be involved for…
• Information? • Creativity? • Approval? • Development?
• Analysis? • Commitment? • Implementation?
Who will document our process and results?
What evidence do we have…?
What different deviations, decisions,
or plans are part of this concern?
How will we know the potential problem has occurred?
What will activate each contingent action?
What will we do if this potential problem happens?
What will minimize the effects if the potential problem happens?
Do we need further clarification?
Do we have a deviation? Is cause unknown?
Do we need to know the cause of a deviation?
Do we need to make a choice?
Do we have an action or plan to protect (enhance)?
What do we need to do about the concern?
What additional analysis is needed?
What needs to be done and when?
Who needs to be involved for…
• Information? • Creativity? • Approval? • Development?
• Analysis? • Commitment? • Implementation?
Who will document our process and results?
What evidence do we have…?
What different deviations, decisions,
or plans are part of this concern?
How will we know the potential problem has occurred?
What will activate each contingent action?
What will we do if this potential problem happens?
What will minimize the effects if the potential problem happens?